## Sheet1
County | Urban area | Authorisation number | Proposed action plan | Proposed date to complete action plan | Priority issues
[5 empty] | No treatment - discharging raw sewage | Inadequate treatment - failed EU treatment standards | Inadequate collecting system (sewers) - failed EU requirements | Significant pressure on waters at risk of pollution | Improvement required to protect endangered pearl mussels | Contributed to poor quality bathing water
Carlow | Tullow | D0091-01 | Improvements completed - monitoring required to assess effectiveness | Completed - monitoring is ongoing to assess effectiveness of improvements |  |  |  | Yes
Cavan | Bailieborough | D0085-01 | Upgrade the treatment plant | 2027 Q4 |  |  |  | Yes
Cavan | Blacklion | D0498-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Cavan | Mullagh | D0252-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Clare | Ballyvaughan | D0327-01 | Build a new treatment plant | 2027 Q3 | Yes
Clare | Kilkee | D0078-01 | Build a new treatment plant | 2027 Q4 | Yes
Clare | Kilmihil | A0091-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Clare | Lahinch | D0080-01 | Upgrade the treatment plant | 2029 Q4 |  | Yes
Cork | Ballycotton | D0516-02 | Build a new treatment plant | 2024 Q4 | Yes
Cork | Ballydesmond | A0326-01 | Upgrade the treatment plant | 2030 |  |  |  |  | Yes
Cork | Boherbue | D0437-01 | Upgrade the treatment plant | 2024 Q1 |  |  |  |  | Yes
Cork | Castletownroche | D0293-01 | Improvements completed - monitoring required to assess effectiveness | Completed - monitoring is ongoing to assess effectiveness of improvements |  |  |  |  | Yes
Cork | Cecilstown | A0319-01 | Improvements completed - monitoring required to assess effectiveness | Completed - monitoring is ongoing to assess effectiveness of improvements |  |  |  |  | Yes
Cork | Cloyne | D0298-01 | Action plan required from Uisce Éireann | Completion date required from Uisce Éireann |  | Yes
Cork | Cork City | D0033-01 | 1. Upgrade the waste water collecting system 2. Action plan to address pressure on waters at risk of pollution required from Uisce Éireann | Completion dates required from Uisce Éireann |  |  | Yes | Yes
Cork | Fermoy | D0058-01 | Upgrade the waste water collecting system | 2024 Q4 |  |  | Yes
Cork | Inchigeelagh | A0349-01 | Improvements completed - monitoring required to assess effectiveness | Completed - monitoring is ongoing to assess effectiveness of improvements |  |  |  |  | Yes
Cork | Kanturk | D0203-01 | Upgrade the treatment plant | 2031 |  |  |  |  | Yes
Cork | Kealkill | A0398-01 | Upgrade the treatment plant | 2031 |  |  |  |  | Yes
Cork | Lombardstown | A0327-01 | Upgrade the treatment plant | 2031 |  |  |  |  | Yes
Cork | Mallow | D0052-01 | Improvements completed - monitoring and assessment required to determine effectiveness | Completed - monitoring is ongoing to assess effectiveness of improvements |  |  | Yes |  | Yes
Cork | Midleton | D0056-01 | Upgrade the waste water collecting system | 2029 Q4 |  |  | Yes
Cork | Rathcormac | D0200-01 | Improve the operation of the treatment plant | 2024 Q2 |  | Yes
Cork | Whitegate - Aghada | D0423-02 | Build a new treatment plant | 2024 Q3 | Yes
Donegal | Bridgend | D0532-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Donegal | Buncrana | D0125-01 | Upgrade the waste water collecting system | 2026 Q2 | [5 empty] | Yes
Donegal | Burnfoot | D0531-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Donegal | Falcarragh | D0343-01 | Build a new treatment plant | 2030 | Yes
Donegal | Kilmacrennan | D0513-01 | Upgrade the treatment plant | 2026 Q1 |  |  |  | Yes
Donegal | Milford | D0342-01 | Build a new treatment plant for Ramelton, Rathmullan and Milford | 2025 Q2 |  |  |  | Yes
Donegal | Moville | D0212-01 | Build a new treatment plant | 2030 | Yes | Yes
Donegal | Ramelton | D0341-01 | Build a new treatment plant for Ramelton, Rathmullan and Milford | 2025 Q2 | Yes
Donegal | Rathmullan | D0345-01 | Build a new treatment plant for Ramelton, Rathmullan and Milford | 2025 Q2 | Yes
Dublin | Balbriggan | D0023-01 | Upgrade the waste water collecting system | 2024 Q2 | [5 empty] | Yes
Dublin | Dublin (Ringsend) | D0034-01 | 1. Upgrade the treatment plant 2. Connect the Howth (Doldrum Bay) area to Ringsend treatment plant 3. Action plans to address pressure on waters at risk of pollution and to protect bathing waters required from Uisce Éireann | 2025 2027 Q2 Completion date required from Uisce Éireann | Yes | Yes |  | Yes |  | Yes
Dublin | Malahide | D0021-01 | Action plan required from Uisce Éireann | Completion date required from Uisce Éireann |  | Yes |  | Yes
Galway | Athenry | D0193-01 | Upgrade the treatment plant | 2031 |  |  |  | Yes
Galway | Ballymoe | A0105-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Galway | Carraroe | D0388-01 | Build a new treatment plant | 2030 | Yes
Galway | Loughrea | D0194-01 | Upgrade the treatment plant | 2031 |  |  |  | Yes
Galway | Mountbellew | D0219-01 | Upgrade the treatment plant | 2027 Q3 |  |  |  | Yes
Galway | Roundstone | A0115-01 | Build a new treatment plant | 2029 Q3 | Yes
Kerry | Abbeydorney | D0417-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Kerry | Kilgarvan | A0065-01 | Upgrade the treatment plant | 2031 |  |  |  |  | Yes
Kerry | Tralee | D0040-01 | Upgrade the waste water collecting system | 2035 |  |  |  | Yes
Laois | Ballyroan | D0385-01 | Upgrade the treatment plant | 2030 |  |  |  |  | Yes
Laois | Castletown | D0387-01 | Improvements completed - monitoring required to assess effectiveness | Completed - monitoring is ongoing to assess effectiveness of improvements |  |  |  |  | Yes
Laois | Portarlington | D0158-01 | Upgrade the waste water collecting system | Completion date required from Uisce Éireann |  |  |  | Yes
Leitrim | Mohill | D0277-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Limerick | Foynes | D0502-01 | Build a new treatment plant | 2028 Q2 | Yes
Limerick | Glin | D0504-01 | Build a new treatment plant | 2028 Q2 | Yes
Limerick | Hospital | D0314-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Limerick | Limerick | D0013-01 | Improvements completed - monitoring required to assess effectiveness | Completed - monitoring is ongoing to assess effectiveness of improvements |  | Yes
Louth | Dundalk | D0053-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Louth | Dunleer | D0111-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Mayo | Newport | D0224-01 | Build a new treatment plant | 2030 | Yes
Monaghan | Carrickmacross | D0062-01 | Relocate the discharge and upgrade the treatment plant | 2024 Q1 to relocate discharge; 2031 for plant upgrade |  |  |  | Yes
Monaghan | Castleblayney | D0205-01 | Treatment plant upgrade completed - monitoring required to assess the effectiveness of the upgrade | Completed - monitoring is ongoing to assess effectiveness of improvements |  |  |  | Yes
Offaly | Kilcormac | D0225-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Roscommon | Roscommon | D0116-01 | Upgrade the waste water collecting system | 2024 Q1 |  |  | Yes
Tipperary | Ballina-Killaloe | D0189-01 | Action plan required from Uisce Éireann | Completion date required from Uisce Éireann |  | Yes
Tipperary | Mullinahone | D0456-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Waterford | Dungarvan | D0017-01 | Upgrade the waste water collecting system | 2033 |  |  |  | Yes
Waterford | Kill | A0380-01 | Upgrade the treatment plant | 2031 |  |  |  | Yes
Westmeath | Athlone | D0007-01 | Upgrade the waste water collecting system | 2025 Q3 |  |  | Yes
Westmeath | Ballymore | D0509-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Wexford | Ballycanew | D0402-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Wexford | Ferns | D0169-01 | Upgrade the treatment plant | 2031 |  |  |  | Yes
Wicklow | Arklow | D0006-02 | Build a new treatment plant | 2025 Q3 | Yes | Yes
Wicklow | Aughrim | D0222-01 | Action plan required from Uisce Éireann | Completion date required from Uisce Éireann |  | Yes
Wicklow | Avoca | D0411-01 | Build a new treatment plant | 2025 Q4 | Yes
Wicklow | Kilcoole | D0087-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Wicklow | Kilpedder | D0416-01 | Upgrade the treatment plant | 2030 |  |  |  | Yes
Total | 73 |  |  |  | 16 | 10 | 6 | 34 | 12 | 3